## Spirint Plan
Spirint Plan for TalkMD Provider Side (Major Changes)
Friday | Sprint Planning where changes are assigned to developers and its lead and developer responsibility to identify dependencies.
Saturday | Developer start their development (Discuss complete change with the Lead and analyst any concern question must be identified at this stage)
Sunday | Offical Holiday
Monday | Developer will be developing the change
Tuesday | Developer will be developing the change
Wednesday | Developer will be developing the change
Thursday | Changes Must be move to the QA on local Links
Friday | Changes must be in QA
Saturday | Review Request Must be generated and got sign off from reviewer on this day of sprinit
Sunday | Offical Holiday
Monday | Changes Must be move to the QA on Testing Links
Tuesday | Changes must be in QA
Wednesday | Changes Must be move to the QA on Staging Links and must be merged to live after sign off from the QA
Thursday | Changes will be deliver to Live Enviornment
Spirint Plan for TalkMD Provider Side (Minior Changes)
Friday | Sprint Planning where changes are assigned to developers and its lead and developer responsibility to identify dependencies.
Saturday | Developer start their development (Developer Must complete those bugs in one day)
Sunday | Offical Holiday
Monday | Changes Must be move to the QA on local Links and review request must be generated and got signed off from reviewer on same day
Tuesday | Changes Must be move to the QA on Testing Links
Wednesday | Changes Must be move to the QA on Staging Links and must be merged to live after sign off from the QA
Thursday | Changes will be deliver to Live Enviornment

## Sprint Log
Developer Name
QA Name
Reviwer Name
Sr | Changes Status | Description | Date | Day | Time
1 | Completed Development
2 | Emailed to QA lead to assign QA resoruce on Change on Local Link
3 | QA lead assign change to its resource
4 | Resource First iteration Email received by developer
5 | Changes Moved for reviwer
6 | Response got from the reviwer response
7 | Cleared reviwe of the change
8 | Moved to testing environment (QA mail generated after verfication)
9 | Signed off mail from the testing envnrionment
10 | Moved to staging environment (QA mail generated after verfication)
11 | Signed off mail from the testing envnrionment
12 | Live merging date